## 1. Product Overview
Item | Description
Product Name | AI Tailoring Measurement Tool
Product Vision/ Purpose | To enable accurate, automated body measurements for tailoring/alteration using user photographs and AI.It eliminates manual measurement, improve accuracy and user experience in tailoring and clothing fit.
Business Goals / Key Success factors | Reduce return rates for online clothing, enhance customer satisfaction, save time for tailors. High landmark accuracy, easy UI, universal object detection, scale calculation reliability.
Primary Stakeholders | End customers, tailors, clothing brands, e-commerce platforms, developers.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Image Upload | US1 | As a user, I want to upload front and side photos with a reference object for accurate measurement. | Support image upload, F/E validation | Must Have | 5 | To Do | Frontend Dev | Upload + error test, bad angle rejection | QA Engineer
E2 | Object Boundary Detection | US2 | As a user, I want the app to recognize and outline my reference object for scale accuracy. | RNN implementation, boundary overlay UX | Must Have | 8 | To Do | AI/Backend | Validate boundary,test various shapes | AI/ML QA Team
E3 | Landmark Detection | US3 | As a user, I want the app to identify and highlight my body landmarks (shoulder, waist, etc). | CNN/MediaPipe/OpenPose integration | Must Have | 13 | To Do | AI/Backend | Keypoint accuracy,missing points handling | AI/ML QA Team
E4 | Pixel-to-Scale Ratio | US4 | As a user, I want measurements to be scaled accurately to real-world units using my reference object. | Scale calculation logic, manual override if needed | Must Have | 8 | To Do | AI/Backend | Compare measures against known standards | AI/ML QA Team
E5 | Measurement Calculation | US5 | As a user, I want to see my actual body measurements displayed clearly. | Measurement logic, error margin display | Must Have | 5 | To Do | Frontend Dev | UI display,logical consistency | QA Engineer
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Photo upload, authentication | None | Completed
v0.2 | 2025-11-22 | Object detection, keypoint detection, auto capture | API access | Completed
v0.3 | 2025-11-29 | Scale computation | AI accuracy | Completed
v0.4 | 2025-12-06 | Measurement calculation, display, live capture | UX feedback | In progress
v1.0 | 2025-12-20 | Full MVP | All of the above | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead
Model recognized most common reference objects accurately. | Some photos with poor lighting led to landmark errors. | Enforce lighting guidelines in user instructions. | Frontend
Code integration between backend AI and UI was smooth. | RNN reference boundary sometimes missed unusual objects. | Collect more reference data, retrain RNN. | AI Lead
User feedback on measurement display was positive. | Some users found uploading side photo confusing. | Improve photo upload UX, add side-guide overlay. | UI/UX